## Introduction
This is the Project Tracker
You will use this to track your work on your project. The first step is to identify your team on the Team sheet. Also on the Team Sheet, you will specify the address of your GitHub repository for the project. After that, you will complete the Features sheet, which is a summarized version of the use cases you wrote for the last assignment. In addition to listing summary versions of your use cases, recall that you also listed in your Business Requirements document various resources users will need to use your product, so include as "features" the task of creating such resources so you can allocate time to making them.
Then you will identify, in helpful detail, the tasks you will perform to implement each feature. You have to be detailed here, thinking very clearly about what it will take to pursue each task in terms of time.
AFter that, on the Test Plans sheet, you will describe how you will test that each feature is working. Finally, on the Work Log tab, you will enter entries for each work session you spend building your project. Include links to particular assets in your GitHub respository that I can refer to to see evidence of your work.
The purpose of this sheet is to serve as a guide and a tracking mechanism as you try to build the various features of your project.

## Team
Team Members
Team member name | Email address
Connor Sweeney | connorrsweeney@lewisu.edu
One Member
Project GitHub | https://github.com/connorswe22/Dungeonmancer
Just list the names and email addresses of the members that comprise this team. If there is only one person, just specify one name and email address.

## Features
Feature List
Feature ID | Feature Name | Feature Description
1 | Tutorial | A tutorial for new users to walk them through their first character.
2 | Pages of steps | Different pages will allow users to fill out different parts of their Character Sheet.
3 | Character Manager | Users will be able to view a list of their created characters and choose to enter the editing page, delete, or simply view their Character Sheet.
4 | Character Editor | Users will access the Editor from the Manager page and be able to edit their pre-existing characters. This is useful for levelling up pre-existing characters.
5 | Character Play Mode | Users will be able to play D&D live with their character sheet in the program, allowing them to perform ability checks and attack rolls right from the program.
6 | Homebrew Creator | Users will be able to add their own homebrew classes, backgrounds, and races to the character creator pages, which can then be used for future characters.
Here we list the specific features of your final project. This is just an alternative way to express what you did for the last assignment. Features are the things your project offers the user, so focus on what the user will experience. What will the user be able to do? How will they interact with what you are building? What will they see when they use what you are building?
For each feature, specify a Feature ID. Perhaps this is just a number, or maybe its a short abbreviation that you'll use to uniquely identify each feature. Then specify a name for the feature that describes cleaerly what it concerns. Finally, offer a very specific but brief description. You already did this in the preceding assignment, but if you weren't specific there, you need to be specific here. Otherwise, you can copy the use case text you wrote in that last assignment. The description you provide here should give us a clear understanding of what the user will be able to do and see and interact with in your product.

## Task Estimation
Task Estimation
Feature ID | Task ID | Task Name | Task Description | Estimated Hours | ID of tasks this depends on | Assigned team members
| 1 | Initial UI Development | The UI must be created in order to swap between creation and managing pages, even if they are blank for now. | 1 |  | All Connor Sweeney
2 | 2 | Class Page | The first page in the steps pages is the class page. UI must be designed in a selection structure, allowing users to only choose one class or make a homebrew one, which can be designed later | 2 | 1 | All Connor Sweeney
2 | 3 | Race Page | This is where users will choose their character's race (species) and will function very similarly to the Class Page, so many aspect may be reused. | 1 | 1, 2 | All Connor Sweeney
2 | 4 | Background Page | After choosing a race and background, users will be directed to choose a background for their character. This adds several other bonuses to the character based on their previous occupation. The page itself will likely function similar to the Class and Race page, so aspects may be reused again. | 1 | 1, 2, 3 | All Connor Sweeney
2 | 5 | Abilities Page | Users will be prompted to assign their ability scores. The default values will be the optimized numbers but players can set their own scores, choose to randomize them, or roll dice to determine them. | 2 | 1 | All Connor Sweeney
2 | 6 | Finalize Character | Users will be able to view their final character sheet at the end of the creation process and make any necessary manual changes they'd like to it before saving it, at which point they will be taken to the management screen. | 1 | 1, 2, 3, 4, 5 | All Connor Sweeney
2 | 7 | Management Screen | Users will be able to view a searchable and sortable list of their saved characters. Users will also be able to be taken to the editing screen if they select to edit a character, or delete a character if they wish, though this will require a confirmation popup to prevent accidental deletions. | 3 | 1, 2, 3, 4 | All Connor Sweeney
4 | 8 | Editing Screen | Users will be able to edit their character's stats directly from this page, in case of a level-up in-game, or acquiring a new weapon or spell | 3 | 1, 2, 3, 4 | All Connor Sweeney
6 | 9 | Homebrew Creator | Users will be able to create homebrew Classes, Races, and Backgrounds through a form that must be completely filled out before applying it to a character. The form will include the background's benefits and a short description of the background, as well as it's name. | 3 | 1 | All Connor Sweeney
| 10 | Character Play Screen | Upon selecting a character's name from the character list, a user will be able to access it in "Play Mode", where a user will be able to perform attack rolls and skill checks, with the characters bonuses applied automatically. | 3 | 1, 2, 3, 5, 7, 9 | All Connor Sweeney
Here we list the tasks you estimate will be needed to complete your project (in other words, to implement its features). Each row represents a task.
For each task, specify the ID of the corresponding feature. These should come from the list of features you provided on the Features sheet, so perhaps use an Excel formula to set them. Then specify the ID of this task. Perhaps it's just a number, or maybe it's an abbreviation, or maybe it's a combination of the feature ID and a number or a letter - for example, if the feature ID is 1 and you want to represent that this is the first task for implementing feature 1, perhaps you could set the Task ID as 1.1 or 1.A.
Next, specify a Task Name. It should clearly but briefly describe what this task concerns.
Next, describe clearly what is needed to accomplish this task. What steps will you take to carry it out
Then specify how many hours it will take to complete the task. This is just an estimate at this point. If this task depends on another task being done, indicate the task ID of the task it depends on in the next column. Finally, specify who is responsible for completing the task. This could be multiple team members if two or more people are needed to complete the task.
Make sure you in include in your time estimate for each task some time for testing that the task was done correctly / is producing the right output. A good rule of thumb is to allot an additional amount of about 20% to 25% of the time it took to do a task for testing that it works. You won't be testing every single task, and the test plans on the test plans sheet will connect to the overall features rather than the individual tasks. Nevertheless, if you follow the rule of thumb that 20% to 25% of your work effort should be added for testing, you will be sure to allow the right amount of time for it.

## Test Plans
Test plans
Feature ID | Test ID | Test Name | Test Description | Tester | Successful outcome
On this sheet, describe how you will test each feature. Each row represents a test you will conduct. You might have multiple tests for each feature to confirm that that feature is working.
In the first column, specify the ID of the feature listed on the Features sheet that this test corresponds to.
In the Test ID column, give this test a unique id. Perhaps it is a combination of the feature ID and a number or letter or abbreviation for this particular test. For example, if the related feature is ID # 1, and this is the first test for ID #1, perhaps the test ID should be 1.1 or 1.A. But you can choose your own unique id system.
In the Test Name column, specify a clear, concise name for this test.
In the Test Description column, specify a clear, concise, but complete description of how the test will be conducted.
In the Tester column, indicate the names of the people on the team who will conduct the test.
Finally, in the Successful Outcome column, describe how you will know that your work passed this test. In other words, how will know that your work successfully implemented the feature it supports?

## Work Log
Task ID (from Task Estimation Sheet) | Date the work was done | Time spent (hours) | Work done by whom? | Description of what was done (be claar in describing the work you did. A step-by-step description would be good.) | Document on GitHub that provides more detail about what was accomplished through this task.